## Basic Manual Gantt Chart
Task Name | Start Date | End Date | Duration
졸업프로젝트 | 2016-11-28 | 2017-10-31 | 337
간트차트 | 2017-01-16 | 2017-01-18 | 2
졸프전시 | 2017-09-15 | 2017-09-30 | 15
출전자격테스트 | 2017-01-01 | 2017-05-31 | 150
Sift, Surf 스터디 | 2017-01-01 | 2017-01-31 | 30
UI구현 | 2017-02-01 | 2017-02-17 | 16
영상처리 구현 | 2017-02-10 | 2017-02-24 | 14
임계값 설정 | 2017-02-17 | 2017-02-24 | 7
테스트 | 2017-02-24 | 2017-02-28 | 4
발표자료 제작 | 2017-03-01 | 2017-03-08 | 7
유지 보수 | 2017-03-27 | 2017-04-07 | 11
대전대회 | 2017-06-26 | 2017-08-21 | 56
개발환경 구축 | 2017-05-01 | 2017-05-08 | 7
로봇 HW이해 | 2017-06-26 | 2017-07-05 | 9
응용 SW설계 | 2017-06-26 | 2017-07-08 | 12
응용 SW설계 | 2017-07-09 | 2017-07-23 | 14
모션 SW구현 | 2017-07-09 | 2017-08-07 | 29
테스트 | 2017-07-23 | 2017-08-14 | 22
일산대회 | 2017-08-15 | 2017-09-15 | 31

## Gantt Chart - Manual End Date
Task Name | Start Date | End Date | Duration (Days) | Days Complete | Days Remaining | Percent Complete | Start Date in Number Form | 42576 | Use this number for the Minimum Bound of the Horizontal Axis to set the beginning of the chart.
Task One | 2016-07-25 | 2016-07-30 | 5 | 2.5 | 2.5 | 50%
Task Two | 2016-07-27 | 2016-08-01 | 5 | 3.75 | 1.25 | 75%
Task Three | 2016-07-27 | 2016-08-04 | 8 | 2 | 6 | 25%
Task Four | 2016-07-29 | 2016-08-06 | 8 | 8 | 0 | 100%
Task Five | 2016-08-01 | 2016-08-09 | 8 | 6 | 2 | 75%
Task Six | 2016-08-01 | 2016-08-05 | 4 | 1.4 | 2.6 | 35%
Task Seven | 2016-08-03 | 2016-08-10 | 7 | 1.75 | 5.25 | 25%
Task Eight | 2016-08-05 | 2016-08-12 | 7 | 4.9 | 2.1 | 70%
Task Nine | 2016-08-03 | 2016-08-09 | 6 | 0.9 | 5.1 | 15%
Task Ten | 2016-08-06 | 2016-08-10 | 4 | 2.4 | 1.6 | 60%
Task Eleven | 2016-08-07 | 2016-08-13 | 6 | 3.9 | 2.1 | 65%
Task Twelve | 2016-08-10 | 2016-08-16 | 6 | 1.5 | 4.5 | 25%
Task Thirteen | 2016-08-14 | 2016-08-19 | 5 | 1.5 | 3.5 | 30%
Task Fourteen | 2016-08-15 | 2016-08-23 | 8 | 4 | 4 | 50%
Task Fifteen | 2016-08-16 | 2016-08-26 | 10 | 4 | 6 | 40%
Task Sixteen | 2016-08-17 | 2016-08-28 | 11 | 3.85 | 7.15 | 35%
Task Seventeen | 2016-08-18 | 2016-08-29 | 11 | 1.65 | 9.35 | 15%
[7 empty] | Key: | Calculated Cell |  | Manual Entry Cell
[8 empty] | These cells will be automatically calculated based on the inputs on other cells. |  | These cells require manual input so the calculated cells have data to work with.

## Gantt Chart - Manual Duration
Task Name | Start Date | End Date | Duration (Days) | Days Complete | Days Remaining | Percent Complete | Start Date in Number Form | 42576 | Use this number for the Minimum Bound of the Horizontal Axis to set the beginning of the chart.
Task One | 2016-07-25 | 2016-07-30 | 5 | 2.5 | 2.5 | 50%
Task Two | 2016-07-27 | 2016-08-01 | 5 | 3.75 | 1.25 | 75%
Task Three | 2016-07-27 | 2016-08-04 | 8 | 2 | 6 | 25%
Task Four | 2016-07-29 | 2016-08-06 | 8 | 8 | 0 | 100%
Task Five | 2016-08-01 | 2016-08-09 | 8 | 6 | 2 | 75%
Task Six | 2016-08-01 | 2016-08-05 | 4 | 1.4 | 2.6 | 35%
Task Seven | 2016-08-03 | 2016-08-10 | 7 | 1.75 | 5.25 | 25%
Task Eight | 2016-08-05 | 2016-08-12 | 7 | 4.9 | 2.1 | 70%
Task Nine | 2016-08-03 | 2016-08-09 | 6 | 0.9 | 5.1 | 15%
Task Ten | 2016-08-06 | 2016-08-10 | 4 | 2.4 | 1.6 | 60%
Task Eleven | 2016-08-07 | 2016-08-13 | 6 | 3.9 | 2.1 | 65%
Task Twelve | 2016-08-10 | 2016-08-16 | 6 | 1.5 | 4.5 | 25%
Task Thirteen | 2016-08-14 | 2016-08-19 | 5 | 1.5 | 3.5 | 30%
Task Fourteen | 2016-08-15 | 2016-08-23 | 8 | 4 | 4 | 50%
Task Fifteen | 2016-08-16 | 2016-08-26 | 10 | 4 | 6 | 40%
Task Sixteen | 2016-08-17 | 2016-08-28 | 11 | 3.85 | 7.15 | 35%
Task Seventeen | 2016-08-18 | 2016-08-29 | 11 | 1.65 | 9.35 | 15%
[7 empty] | Key: | Calculated Cell |  | Manual Entry Cell
[8 empty] | These cells will be automatically calculated based on the inputs on other cells. |  | These cells require manual input so the calculated cells have data to work with.